## User stories
| MAIN STORY | SUB-TASK
1 | Authentication Service | Add User
Update User
Delete User
View All Users
2 | Booking service | Add a Booking
Update booking
View Booking details
Cancel a Booking
3 | Route Service | Find Flight by Source and destination
Find all Airports
4 | Schedule Service | View A Scheduled Flight
Update Scheduled Flight
Delete A Scheduled Flight
5 | Flight Service | Add a Flight
View a Flight
Delete a Flight
Update a Flight
6 | Consumer Service | Connect all services

## Vikas
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Schedule Service
1.1 | Get a Scheduled Flight
1.1.1 | Html Page | 1 | 1 | Saturday
1.1.2 | Service + Controller Function | 1.5 | 1.5 | Saturday
1.1.3 | Exception Handling | 1 | 1 | Tuesday
1.2 | Update Scheduled Flight
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Service + Controller Functions | 1.5 | 1.5 | Saturday
1.2.3 | Exception Handling | 1 | 1 | Tuesday
1.3 | Delete a Scheduled Flight
1.3.1 | Html Page | 1 | 1 | Monday
1.3.2 | Service + Controller Functions | 1.5 | 1.5 | Monday
1.3.3 | Exception Handling | 1 | 1 | Tuesday
1.4 | Show All Scheduled Flights
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Service + Controller Functions | 1.5 | 1.5 | Monday
1.4.3 | Exception Handling | 1 | 1 | Tuesday
1.5 | Registration + Login + Logout
1.5.1 | Html Page | 2 | 2 | Wednesday
1.5.2 | Component | 2 | 2 | Wednesday
1.5.3 | Functions | 1 | 1 | Wednesday
1.5.4 | Integration with backend | 1 | 1 | Wednesday

## Thouseef
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Booking
1.1 | Add a Booking
1.1.1 | Html Page | 1 | 1 | Saturday
1.1.2 | Service + Controller Function | 1.5 | 1 | Saturday
1.1.3 | Exception Handling | 1 | 2 | Wednesday
1.2 | Update a booking
1.2.1 | Html Page | 1 | 1 | Monday
1.2.2 | Service + Controller Function | 1 | 1 | Monday
1.2.3 | Exception Handling | 2 | 2 | Monday
1.3 | View booking details
1.3.1 | Html Page | 1 | 1 | Monday
1.3.2 | Service + Controller Function | 1 | 1 | Monday
1.3.3 | Exception Handling | 3 | 3 | Monday
1.4 | Cancel booking details
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Service + Controller Function | 1 | 1 | Monday
1.4.3 | Exception Handling | 2 | 2 | Monday
2 | Flight
2.1 | Add a Flight
2.1.1 | Html Page | 1 | 1 | Saturday
2.1.2 | Service + Controller Function | 1 | 1 | Saturday
2.1.3 | Exception Handling | 2 | 2 | Wednesday
2.2 | View a Flight
2.2.1 | Html Page | 1 | 1 | Saturday
2.2.2 | Service + Controller Function | 1 | 1 | Saturday
2.2.3 | Exception Handling | 2 | 2 | Wednesday
2.3 | Delete a Flight
2.3.1 | Html Page | 1 | 1 | Saturday
2.3.2 | Service + Controller Function | 1 | 1 | Saturday
2.3.3 | Exception Handling | 2 | 2 | Wednesday
2.4 | Update a Flight
2.4.1 | Html Page | 1 | 1 | Saturday
2.4.2 | Service + Controller Function | 1 | 1 | Saturday
2.4.3 | Exception Handling | 2 | 2 | Wednesday

## Rohan
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Route Service
1.1 | Find Flight by Source and destination
1.1.1 | HTML Page | 3 | 3 | Saturday
1.1.2 | Service + Controller | 1 | 1 | Saturday
1.1.3 | Exception Handling | 2 | 2 | Tuesday
1.2 | Find all Airports
1.2.1 | HTML Page | 3 | 3 | Saturday
1.2.2 | Service + Controller | 1.5 | 1.5 | Saturday
1.2.3 | Exception Handling | 1.5 | 1.5 | Tuesday
2 | Consumer Service
2.1 | Html Page | 2 | 2 | Wednesday
2.2 | Connecting all services | 2 | 2 | Wednesday
2.3 | Functions | 1 | 1 | Wednesday
2.4 | Integration with backend | 1 | 1 | Wednesday